## Sheet1
ID | Major Milestones |  |  | Planned Duration | Planned Start Date | Planned Finish Date | Actual Duration | Actual Start Date | Actual Finish Date | Actual % Complete | Planned % Completion | Variance in Days | Responsible
1 | Database Designing | Project Designing | Project Designing
2 |  | Design Wireframes | Design Wireframes
3 | Web API Development | Project Designing | Project Designing
4 |  | Design Wireframes | Design Wireframes
5 | Project Designing | Project Designing | Project Designing
6 | Design Wireframes | Design Wireframes | Design Wireframes | 3
7 | Application Screens Designing on Photoshop | Design Wireframes | Design Wireframes | 3
8 | UI Tools and Color Themes | Design Wireframes | Design Wireframes | 3
9 | Project Development | Project Development | Project Development
10 | Alpha Application:
11 | User Interface Designing and Functionality | User Interface Designing for iOS | User Interface Designing for iOS
12 | PHASE - I (Login and Employee Selection)
13 | Welcome Screen |  |  | 1
14 | Login |  |  | 1
15 | Dashboard
16 | Home (Department, Search Employee, Stats) |  |  | 1
17 | Employee Selection
18 | List of Departments |  |  | 1
19 | List of Employees |  |  | 1
20 | Search Employee |  |  | 1
21 | Filter Employees/ Filter Departments |  |  | 1
22 | Employee Assessment Detail |  |  | 1
23 | Add new Assessment |  |  | 1
24 | Stats (Outcome) |  |  | 2
25 | Overall population outcome will display
26 | PHASE - II (Employee Self Assessments/Input)
27 | Employee Medical History |  |  | 3
28 | On each Yes question field will be appear (Popup / Expandable List)
29 | Employee Family History |  |  | 0.5
30 | Employee Psycosocial History |  |  | 0.5
31 | Employee Smoking Behavior |  |  | 0.5
32 | PHASE - III (Nurse Input)
33 | Employee Health Summary |  |  | 1
34 | Integration with Patient Profile Viewer |  |  | 2
35 | System will determine whether the Employee needs to be referred to physician displaying the derivations. |  |  | 0.5
36 | Nurse will enter the final decision and close the assessment
37 | Beta Application:
38 | Web Services and Remaining Functionality Integration | User Interface Designing for iOS | User Interface Designing for iOS
39 | Required Web Services | System Deployment | System Deployment
40 | Login (Get User/Nurse Detail in Login Service) | Android App Integration and Functionality Testing | Android App Integration and Functionality Testing | 1
41 | Get overall outcomes (stats) |  |  | 1
42 | Get department list |  |  | 1
43 | get employee list |  |  | 1
44 | Search Employee |  |  | 1
45 | Get Employee Assessment Detail |  |  | 1
46 | Add new Assessment |  |  | 1
47 | Get Employee Assessment Record (Medical, Family, Psycosocial and Smoke behavior) |  |  | 1
48 | Save Employee Assessment Record (Medical, Family, Psycosocial and Smoke behavior) |  |  | 2
49 | Get Patient Profile (Medical Report) |  |  | 1
50 | Save Health Summary (Nurse Input: height, weight etc) |  |  | 1
51 | Get Health Summary (Nurse Input: height, weight etc) |  |  | 1
52 | Save Nurse recommendation of Employee |  |  | 1
53 | System Integration Testing and Functionality Testing | System Integration Testing and Functionality Testing | System Integration Testing and Functionality Testing
54 | App Integration and Functionality Testing | Android App Integration and Functionality Testing | Android App Integration and Functionality Testing | 5
55 | System Deployment | System Deployment | System Deployment
56 | App Publishing in App Store | Android App Publishing in App Store | Android App Publishing in App Store | 3
57
|  |  | Total Duration | 50
Days
Formulas:
Actual Duration = IF([Actual Start Date]="","",IF([Actual Finish Date]="",NETWORKDAYS([Actual Start Date],(F4),AA8:AA78),NETWORKDAYS([Actual Start Date],[Actual Finish Date],AA8:AA78)))
Planned Duration = IF(NETWORKDAYS([Planned Start Date],[Planned Finish Date])=0,"",NETWORKDAYS([Planned Start Date],[Planned Finish Date],AA8:AA78))
Note on H7: Working Days
Note on K7: Working Days

## Alpha
ID | Major Milestones |  |  | Planned Duration | Planned Start Date | Planned Finish Date | Actual Duration | Actual Start Date | Actual Finish Date | Actual % Complete | Planned % Completion | Variance in Days | Responsible
1 | Project Development | Project Development | Project Development
2 | Alpha Application:
3 | User Interface Designing and Functionality | User Interface Designing for iOS | User Interface Designing for iOS
4 | PHASE - I (Login and Employee Selection)
5 | Welcome Screen |  |  | 1
6 | Login |  |  | 1
7 | Dashboard
8 | Home (Department, Search Employee, Stats) |  |  | 1
9 | Employee Selection
10 | List of Departments |  |  | 1
11 | List of Employees |  |  | 1
12 | Search Employee |  |  | 1
13 | Filter Employees/ Filter Departments |  |  | 1
14 | Employee Assessment Detail |  |  | 1
15 | Add new Assessment |  |  | 1
16 | Stats (Outcome) |  |  | 2
17 | Overall population outcome will display
18 | PHASE - II (Employee Self Assessments/Input)
19 | Employee Medical History |  |  | 3
20 | On each Yes question field will be appear (Popup / Expandable List)
21 | Employee Family History |  |  | 0.5
22 | Employee Psycosocial History |  |  | 0.5
23 | Employee Smoking Behavior |  |  | 0.5
24 | PHASE - III (Nurse Input)
25 | Employee Health Summary |  |  | 1
26 | Integration with Patient Profile Viewer |  |  | 2
27 | System will determine whether the Employee needs to be referred to physician displaying the derivations. |  |  | 0.5
28 | Nurse will enter the final decision and close the assessment
|  |  | Total Days | 19
Days
Formulas:
Planned Duration = IF(NETWORKDAYS([Planned Start Date],[Planned Finish Date])=0,"",NETWORKDAYS([Planned Start Date],[Planned Finish Date],AA8:AA49))
Note on H7: Working Days
Note on K7: Working Days

## Beta
ID | Major Milestones |  |  | Planned Duration | Planned Start Date | Planned Finish Date | Actual Duration | Actual Start Date | Actual Finish Date | Actual % Complete | Planned % Completion | Variance in Days | Responsible
37 | Beta Application:
38 | Web Services and Remaining Functionality Integration | User Interface Designing for iOS | User Interface Designing for iOS
39 | Required Web Services | System Deployment | System Deployment
40 | Login (Get User/Nurse Detail in Login Service) | Android App Integration and Functionality Testing | Android App Integration and Functionality Testing | 1
41 | Get overall outcomes (stats) |  |  | 1
42 | Get department list |  |  | 1
43 | get employee list |  |  | 1
44 | Search Employee |  |  | 1
45 | Get Employee Assessment Detail |  |  | 1
46 | Add new Assessment |  |  | 1
47 | Get Employee Assessment Record (Medical, Family, Psycosocial and Smoke behavior) |  |  | 1
48 | Save Employee Assessment Record (Medical, Family, Psycosocial and Smoke behavior) |  |  | 2
49 | Get Patient Profile (Medical Report) |  |  | 1
50 | Save Health Summary (Nurse Input: height, weight etc) |  |  | 1
51 | Get Health Summary (Nurse Input: height, weight etc) |  |  | 1
52 | Save Nurse recommendation of Employee |  |  | 1
|  |  | Total Days | 14
Days
Formulas:
Planned Duration = IF(NETWORKDAYS([Planned Start Date],[Planned Finish Date])=0,"",NETWORKDAYS([Planned Start Date],[Planned Finish Date],AA8:AA37))
Note on H7: Working Days
Note on K7: Working Days